## Milestone
Enterprise Data Quality Project |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  |  | Oct
Task ID | Task Name | % Complete | W01 | W02 | W03 | W04 | W01 | W02 | W03 | W04 | W01 | W02 | W03 | W04 | W01 | W02 | W03 | W04 | W05 | W01 | W02 | W03 | W04 | W05 | W01 | W02 | W03 | W04
1 | Requirement
1.1 | Requirement for 60 KDEs | 100% | May W03: 100%
1.2 | Requirement for Macth/Merge and Deduplication | 100% | May W02: 100%
1.3 | Requirement for 3 OAS | 100% | May W03: 100%
2 | Design
2.1 | Completes design for 60 KDEs | 100% | Jun W01: 100%
2..2 | Completed design DR & HA | 100% | May W02: 100%
2.3 | Completed design OAS reports | 100% | Jun W01: 100%
2.4 | Completed design Match/Merge | 100% | Jun W01: 100%
2.5 | Completed design ODI/CM | 100% | Jun W01: 100%
2.6 | Docunent Delivereble (KDEs, DR&HA, OAS,MM &ODI/CM) | 50% | Jul W04: 50%
3 | Implement | 100%
3.1 | Implement 30/30 KDEs (Sprint 1) | 100% | May W04: 100%
3.2 | Implement 12/22 KDEs (Sprint 2) | 100% | May W04: 100%
3.3 | Implement 18/48 KDEs (Sprint 3) | 100% | Jun W01: 100%
3.4 | Implement case management | 100% | Jun W03: 100%
3.5 | Implement ODI for EDQ job | 100% | Jun W03: 100%
3.6 | Implement OAS | 100% | Jun W02: 100%
3.7 | Implement Match & Merge | 100% | Jun W01: 100%
4 | SIT
4.1 | SIT for 69 KDEs | 100% | Jun W02: 100%
4.2 | SIT for Match/Merge and Deduplication | 100% | Jun W04: 100%
4.3 | SIT for 4 OAS | 100% | Jun W04: 100%
4.4 | SIT for ODI/CM | 100% | Jun W04: 100%
5 | UAT | 72.5%
5.1 | UAT for 69 KDEs | 100% | Jun W04: 100%
5.2 | UAT for Match/Merge and Deduplication | 70% | Jul W02: 70%
5.3 | UAT for 4 OAS | 20% | Aug W01: 20%
5.4 | UAT for CM | 100% | Jul W02: 100%
6 | Production | 25%
6.1 | Deploy EDQ jobs | 100% | Aug W02: 100%
6.2 | Deploy Match/Merge | 0% | bar: Sep W04
6.3 | Deploy CM | 0% | bar: Sep W03
6.4 | Deploy OAS | 0% | bar: Oct W02
7 | Golive KDE, CM, MM, OAS | 25% | Aug W02: 25%
8 | Post production assistance | 0% | bar: Oct W03 to Oct W04
KDE
Closure sign off
CM & MM
OAS